## Sheet1
** ASSUMING 2 RESEARCHERS
| Participant 1 | Participant 2 | Participant 3 | Participant 4 | Participant 5 | Participant 6 | Participant 7 | Participant 8 | Participant 9 | Participant 10 | 11 | 12 | 13 | 14
9:00 |  | consent/MMSE
9:30 | CBS | CBS | consent/MoCA | consent/MMSE
10:00 |  |  | CBS | CBS | consent/MoCA
10:30 |  |  |  |  | CBS
11:00
11:30 | [5 empty] | consent/MoCA | consent/MMSE
12:00 | [5 empty] | CBS | CBS | consent/MoCA | consent/MMSE
12:30 | [7 empty] | CBS | CBS | consent/MoCA
1:00 | [9 empty] | CBS
1:30
2:00 | [10 empty] | consent/MoCA | consent/MMSE
2:30 | [10 empty] | CBS | CBS | consent/MoCA | consent/MMSE
3:00 | MMSE | [11 empty] | CBS | CBS
3:30 |  | MoCA
4:00 |  |  | MMSE | MoCA
4:30 |  |  |  |  | MMSE | MMSE
5:00 | [6 empty] | MoCA | MMSE
5:30 | [8 empty] | MoCA | MMSE
6:00 | [10 empty] | MMSE | MoCA
6:30 | [12 empty] | MMSE | MoCA
7:00 | [10 empty] | **Maybe these MMSE sessions are too late and should actually be scheduled for the following day during buffer time between CBS sessions

## Sheet2
2018-02-05
| P101 | P102 | P103 | P104 | P105 | P106 | P107 | P108 | P109 | P110 | P111 | P112 | P113 | P114 | P115
9:00 | 2018-02-05 P101: MOCA; 2018-02-05 P102: MMSE
9:30 | 2018-02-05 P101: CBS; 2018-02-05 P102: CBS; 2018-02-05 P103: MOCA; 2018-02-05 P104: MMSE
10:00 | 2018-02-05 P103: CBS; 2018-02-05 P104: CBS; 2018-02-05 P105: MOCA | Setup CBS tasks on tablets
10:30 | 2018-02-05 P105: CBS | come up with raffle prize
11:00 | 2018-02-05 P106: MMSE; 2018-02-05 P107: MOCA | office is two floors up from large space
11:30 | 2018-02-05 P106: CBS; 2018-02-05 P107: CBS; 2018-02-05 P108: MOCA; 2018-02-05 P109: MMSE
12:00 | 2018-02-05 P108: CBS; 2018-02-05 P109: CBS; 2018-02-05 P110: MOCA
12:30 | 2018-02-05 P110: CBS
1:00
1:30
2:00 | 2018-02-05 P111: MOCA; 2018-02-05 P112: MMSE
2:30 | 2018-02-05 P101: MMSE; 2018-02-05 P102: MOCA; 2018-02-05 P111: CBS; 2018-02-05 P112: CBS; 2018-02-05 P113: MOCA; 2018-02-05 P114: MMSE
3:00 | 2018-02-05 P103: MMSE; 2018-02-05 P104: MOCA; 2018-02-05 P113: CBS; 2018-02-05 P114: CBS; 2018-02-05 P115: MOCA
3:30 | 2018-02-05 P105: MMSE; 2018-02-05 P106: MOCA; 2018-02-05 P115: CBS
4:00 | 2018-02-05 P107: MMSE; 2018-02-05 P108: MMSE
4:30 | 2018-02-05 P109: MOCA; 2018-02-05 P110: MMSE
5:00 | 2018-02-05 P111: MMSE; 2018-02-05 P112: MOCA
5:30 | 2018-02-05 P113: MMSE; 2018-02-05 P114: MOCA; 2018-02-05 P115: MMSE
2018-02-06
| P116 | P117 | P118 | P119 | P120 | P121 | P122 | P123 | P124 | P125 | P126 | P127 | P128 | P129 | P130
9:00 | 2018-02-06 P117: MMSE
9:30 | 2018-02-06 P116: CBS; 2018-02-06 P117: CBS; 2018-02-06 P118: MOCA; 2018-02-06 P119: MMSE
10:00 | 2018-02-06 P118: CBS; 2018-02-06 P119: CBS; 2018-02-06 P120: MOCA
10:30 | 2018-02-06 P120: CBS
11:00 | 2018-02-06 P121: MMSE; 2018-02-06 P122: MOCA
11:30 | 2018-02-06 P121: CBS; 2018-02-06 P122: CBS; 2018-02-06 P123: MOCA; 2018-02-06 P124: MMSE
12:00 | 2018-02-06 P123: CBS; 2018-02-06 P124: CBS; 2018-02-06 P125: MOCA
12:30 | 2018-02-06 P125: CBS
1:00
1:30
2:00 | 2018-02-06 P126: MOCA; 2018-02-06 P127: MMSE
2:30 | 2018-02-06 P116: MMSE/moca; 2018-02-06 P117: MOCA; 2018-02-06 P126: CBS; 2018-02-06 P127: CBS; 2018-02-06 P128: MOCA; 2018-02-06 P129: MMSE
3:00 | 2018-02-06 P118: MMSE; 2018-02-06 P119: MOCA; 2018-02-06 P128: CBS; 2018-02-06 P129: CBS; 2018-02-06 P130: MOCA
3:30 | 2018-02-06 P120: MMSE; 2018-02-06 P121: MOCA; 2018-02-06 P130: CBS
4:00 | 2018-02-06 P122: MMSE; 2018-02-06 P123: MMSE; 2018-02-06 P124: MOCA
4:30 | 2018-02-06 P125: MMSE; 2018-02-06 P126: MMSE
5:00 | 2018-02-06 P127: MOCA; 2018-02-06 P128: MMSE
5:30 | 2018-02-06 P129: MOCA; 2018-02-06 P130: MMSE
2018-02-07
| P131 | P132 | P133 | P134 | P135
9:00 | 2018-02-06 P116: MOCA
9:30 | 2018-02-06 P116: CBS
10:00
10:30 | 2018-02-06 P117: MMSE
11:00 | 2018-02-06 P117: CBS
11:30
12:00 | 2018-02-06 P118: MOCA
12:30 | 2018-02-06 P118: CBS
1:00
1:30 | 2018-02-06 P119: MMSE
2:00 | 2018-02-06 P119: CBS
2:30
3:00 | 2018-02-06 P120: MOCA
3:30 | 2018-02-06 P120: CBS
4:00
4:30 | 2018-02-06 P116: MMSE; 2018-02-06 P117: MOCA
5:00 | 2018-02-06 P118: MMSE; 2018-02-06 P119: MOCA
5:30 | 2018-02-06 P120: MMSE

## Sheet3
ID | Date | Session 1 Time | Session 2 Time | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100